## Slide 1
NCH: Mid Range Programme – Pile Cap Production Plan
Core C
Riser 1
Core B
Core A
Stair 7
Stair 8
Stair 9
SB ZONE 6
CB ZONE 2
CB ZONE 3
EB ZONE 2
EB ZONE 1
Stair 3
Stair 4
FUNDEX RIG SEQUENCING
ENTECCO RIG SEQUENCING
Rig Starting Point
UNCONTROLLED - FOR SEQUENCING INFORMATION ONLY
CB ZONE 1
SB ZONE 1
1
2
3
4
5
6
7
8
9
10
1
2
3
4
5
6
7
1
2
3
4
5
1
2
3
4
1
2
3
4
1
2
4
3
5
6
CB ZONE 4
1
2
3
4
5
6
2
3
4
1
SB ZONE 2
SB ZONE 4
2
1
3
4
1
2
3
5
4
SB ZONE 5
1
2
3
4
5
Stair 10
1
2
3
4
5
SB ZONE 3
WB ZONE 1
WB ZONE 2
WB ZONE 3

## Slide 2
Centre Block (CB)
South Block (SB)
West Block (WB)
East Block (EB)
NCH: MRP (Aug-Oct 12) – Mandatory Completion Milestones (Upper Basement) (Substructure)
EB Zone 1
22-Nov-12
SB Zone 6
SB Zone 5
SB Zone 3
SB Zone 7
SB Zone 1
SB Zone 4
SB Zone 2
SB Zone 8
Crew Starting Area
To Level G00
SB Zone 5
To Level G00
SB Zone 1
SB Crew #2
Start Point
SB Crew #1
Start Point

## Slide 3
Centre Block (CB)
South Block (SB)
West Block (WB)
East Block (EB)
NCH: MRP (Aug-Oct 12) – Mandatory Completion Milestones (Ground Level)
EB Zone 1
14-Dec-12
EB Zone 2
17-Jan-13
EB Zone 3
21-Jan-13
EB Zone 4
18-Feb-13
WB Zone 1
8-Nov-12
WB Zone 2 9-Oct-12
WB Zone 3
728m2
12-Nov-12
SB Zone 6
SB Zone 5
SB Zone 3
SB Zone 7
SB Zone 1
SB Zone 4
CB Zone 1
31-Oct-12
CB Zone 2
6-Nov-12
CB Zone 3
8-Dec-12
CB Zone 5
CB Zone 4
17-Jan-13
SB Zone 2
SB Zone 9
SB Zone 8